## Slide 1
Sustaining Integrity: A Digital Transformation Strategy for Chipotle
KICKOFF MEETING
JUNE 09, 2025
IS478 Group 2 | DePaul University
Chipotle Mexican Grill, Inc.

## Slide 2: KICKOFF MEETING AGENDA
Welcome and Introductions – Meet the Chipotle sponsors and IS478 consulting team
Project Goals and Scope – Understand the focus areas and key objectives
Engagement Overview – Project phases, deliverables, and approach
Timeline and Milestones – Key dates, phases, and final presentation
Collaboration and Communication Plan – Roles, meeting cadence, and stakeholder alignment
Q&A and Next Steps – Open discussion and alignment on immediate actions

## Slide 3: PROJECT TEAM INTRODUCTIONS
Project Sponsors:
Scott Boatwright – CEO, Chipotle Mexican Grill (Executive Sponsor)
Jason Kidd – Engagement Manager, Chipotle Mexican Grill (Day-to-Day Contact)
Consulting Team – IS 478 Group 2:
Priyanka Erande – Executive Sponsor (IS478 Project Advisor & Oversight)
Raghuvarun Kancharla – Client Services Representative (Primary Contact & Client Communication)
Sudipth Saravanan – Project Lead (Strategy & Execution Lead)
Vazeer Khan – Project Delivery Lead (PM & Quality Assurance)
Sparshika Kumar – Stakeholder Engagement Coordinator (Interview & Stakeholder Management)

## Slide 4: STAKEHOLDER COLLABORATION COMMITMENT
All stakeholders will contribute to:
Aligning project outcomes with Chipotle’s strategic vision
Identifying core operational challenges and innovation opportunities
Validating needs, use cases, and proposed strategies
Shaping practical solutions and the implementation roadmap
Maintaining open communication and shared accountability throughout the engagement

## Slide 5: PROJECT GOAL AND SCOPE
Project Goal:
Assess Chipotle’s operational and digital infrastructure.
Enhance workforce management, supply chain resilience, and menu innovation.
Sustain growth while preserving brand principles of sustainability and food integrity.
Project Scope:
Evaluating labor practices and digital tools.
Analyzing ethical sourcing challenges and supplier diversification.
Recommending improvements in customer engagement and digital ordering systems.
Delivering a phased roadmap and success metrics for implementation.

## Slide 6: PROJECT OVERVIEW
Review existing documentation and processes related to HR, supply chain, and digital platforms.
Conduct interviews with stakeholders from HR, operations, and supply chain.
Benchmark Chipotle’s performance against industry best practices.
Design strategic recommendations focused on:
Reducing employee turnover.
Diversifying suppliers to address sourcing risks.
Innovating the digital experience and menu offerings.
Conduct cost-benefit and risk analyses to evaluate solution feasibility.
Prepare KPIs and an implementation roadmap.
Present final recommendations to Chipotle’s executive stakeholders.

## Slide 7: PROJECT TIMELINE
Milestone | Date
Project Kickoff | June 09, 2025
Discovery Phase Begins | June 14, 2025
Stakeholder Interviews | June 30, 2025
Benchmark Analysis | July 15, 2025
Strategy & Roadmap Draft | July 30, 2025
Feedback & Roadmap Finalization | August 20, 2025
Executive Presentation | September 05, 2025
6/9/2025
Duration: ~12 weeks

## Slide 8: ENGAGEMENT COMMUNICATION PLAN
Engagement Communication Guidelines: Weekly Progress Meetings Scheduled team check-ins for status updates, blockers, and feedback alignment.
Project Management & Collaboration Tools: Team Collaboration: Email, Zoom/Teams for virtual meetings (preferred for internal coordination and quick updates)
Client Communications: All client updates and reports will be routed through Jordan (Client Approver) for weekly approvals and alignment. Stakeholder feedback will be integrated during milestone reviews.
Supplier Contact Protocol: IS478 – Group 2 will manage all external communication with potential solution providers. Chipotle team members should redirect any inquiries to: Raghuvarun Kancharla – Client Services Representative.

## Slide 9
Thanks for Participation
Questions, Comments and Feedback